## Sheet1
Week | Goals (What we want to complete by this week) | Ishan accomplishments | Paulo accomplishments | Gabriel accomplishments | Jamie accomplishments | Jace feedback | Changes
2018-10-19 |  | Continued working on Udemy React tutorial, updated timeline | Continued working on Udemy React tutorial, updated timeline | Worked on Udemy React tutorial | Started Udemy tutorial, updated timeline
2018-10-26 | Each person begins to learn React; each person considers which component of the application they'd most like to work on | Continued working on Udemy React tutorial, updated timeline | Completed proprietary React tutorial, filled in Timeline goals | Continued working on Udemy React tutorial | Look into Heroku, completed proprietary React tutorial
2018-11-02 | Learn React, Flask | FALL BREAK | FALL BREAK | FALL BREAK | FALL BREAK
2018-11-09 | Finalize Database Specs, learn React, Flask | -Working through React Udemy course -Organized meeting with app team to clarify work divisions and workflow -Got database specs (almost finalized) | Completed relevant segment of React udemy course, created demo React application, began Flask tutorial | Figured out framework for and stack (React + Flask + MongoDB), and how we would structure the app. Began tutorial for basic end-to-end implementation | Working through React Udemy course, created React application for practice, began tutorial on end-to-end dev React + Flask + MongoDB. Looked at using Heroku with flask |  | - Changed DB framework to Mongo from Postgres
2018-11-16 | Finalize Design Complete Prototype (Dashboard) -set up database, server, and client interaction -host locally (not Heroku) | -Working through React Udemy course -Finalized database specs -Started sketching out backend API | Spearheaded prototype, implementing rudimentary demonstrations of POST/GET requests. Created the DB and led implementation of React front-end and Flask back-end. | -Built frontend for dashboard -hammered out pipenv and dependencies for builds | Developed and debugged end-to-end prototype with POST and GET requests. Continued React Udemy tutorial. Also completed end-to-end tutorial on libraries like axios that helped with creation of our prototype.
2018-11-23 | -backend off the ground -dashboard UI beginnings -host prototype on heroku | -Get backend off the ground | Began working on the dashboard | More react tutorial + did some work on initializing dashboard creation process in react | More react tutorial, looking into individual student landing page
2018-11-30 | ALPHA VERSION -Fully functional Dashboard -Beginnings of Individual student landing page | -adjusted table schemas -worked on defining backend API with Gabe | Implemented dashboard screen and routers routing to user details page. Wired up front-end and back-end and performed testing for demo | Built out backend process for querying MongoDB, which includes sending the user information as a JSON string over the server and overriding the default JSON Encoder in Flask to convert mongo's BSON format to JSON for react compatibility. | Finished essential components of react tutorial and completed appropriate challenges. Also created the individual student goals page (entirely React), and began the process of parsing data from the database to display on the page itself. |  | -dropped a template userId and are using mongo's actual userid's -Jace on Final Version: Have a log-in through CAS with a landing page before people sign-in, create the progress UI page, and spend some time on it (this is the unique part to our app, do some data analysis). "Messaging" button will be replaced by sending email to user.
2018-12-07 | -Connect Individual Student Landing Page to backend (Jamie) -Complete connection of Dashboard to backend (Paulo) -Progress page UI (Gabe) -Finish core backend -- everything besides CAS (Ishan) | -Finished 90% of your moms backend -Finalized database schemas -Populating database | Finished implementing table + sorting + filters on table (waiting on backend implementations to test filters). Started working on Change Goals screen. | Created basic functionality for progress page with mock data | Set up heroku URL and learned process of hosting with React frontend and Flask backend. Also continued work on individual student page with populating parsed data.
2018-12-14 | BETA VERSION -Dashboard has email functionality in the table (Paulo) -Connect Progress to backend (Gabe) -Finish Change Daily Nutrient Targets page (Paulo and Jamie) -Integrate login page UI with CAS (Gabe and Ishan) | -updated backend as necessary for frontend guys | Started and finished login screen. Finished Change Goals page. Worked on Header. Finalized dashboard layout. | Connected progress page with mongo db data, with dynamic visualizations | Got individual student page set up with actual data from the database for all fields after parsing it in, set up front end of the site on heroku and tested potential heroku backend setup across Windows and Mac OS.
2018-12-21 | -Deploy on Heroku -Styling: Jace recommends extra things like shadowing, more colors, make different filters different colors, for the final demo | -updated backend as necessary for frontend guys | Minor styling (began looking into how we would go about making changes to look of each of our pages) | progress page styling, connecting with user id props | Got front end and back-end fully working on heroku
2018-12-28 | HOLIDAY WEEK | -CAS | Major styling. Fully styled Login Page, Dashboard Page, Change Goals Page. Also made bug changes to the change goals page and to the login screen. | Finished Progress Page styling, heroku integration | Integrated master branch into Heroku, continued work on individual student page functionality
2019-01-04 | -Styling | -CAS | Worked on minor changes (e.g. the dashboard watchlist functionality, tweaks to Axios calls, helping Ishan w/ CAS when that was still an objective. | Small bug fixes (i.e. goal display not showing up for bar chart with goal higher than max of series) | Finalized individual student page functionality and styling
1/9/19-1/11/19 | DEMONSTRATION | -CAS and fixing Heroku -deliverables |  | Debugging my own pages along with a few small additions. We actually created the watchlist functionality here at the last second, so I did the coding for that on the dash. | Debugging, added notes textbox, added watchlist functionality, added images + image placeholders for the users
2019-01-15 | FINAL EVERYTHING | -CAS and fixing Heroku -deliverables |  | Helped Ishan with login authorization (in addition to CAS), implemented Error Screen and redirection code, spearheaded user testing, fixed various frontend bugs, completed writing | Fixing final bugs, soliciting user feedback, completing relevant sections of Programmer's guide
Notes: Get some user feedback from some people (friends, nutritionists)